## Slide 1
AURORA DYNAMICS
Project Northstar August QBR
Meridian Bank and Aurora Dynamics
Presented Wed 12 Aug 2026

## Slide 2
Agenda
Progress since the last QBR
Value delivered to date
Service performance and operating confidence
Phase 3 roadmap and decision points
Customer asks and next actions

## Slide 3
Executive summary
Northstar is progressing with visible operational momentum and an Amber delivery status.
Nine countries have completed deployment and moved into a steadier operating pattern.
Current progress is 1,870 deployed assets out of the 3,200-asset enterprise scope.
The most important delivery dependency is the Italy regulatory approval path.
Aurora Dynamics recommends preserving scope and sequencing carefully rather than compressing quality gates.

## Slide 4
Progress snapshot
Metric | Current position | QBR interpretation
Deployment progress | 1,870 / 3,200 assets | 58% of contracted scope deployed
Country completion | 9 / 14 countries | Completed countries are in operating handover
Firmware distribution | 3.6.0: 1,230; 3.4.2: 640 | Upgrade work remains targeted and manageable
Overall RAG | Amber | Risks are known, owned, and time-bound

## Slide 5
Value delivered
Completed countries now have a common operating pattern for predictive maintenance alerts.
Operations teams can review alert evidence in a consistent structure across completed locations.
Firmware modernization supports a cleaner support model and fewer country-specific exceptions.
The delivery team has reduced ambiguity by using one action register and one risk narrative.
The next value narrative will quantify downtime avoidance in EUR for executive review.

## Slide 6
Service performance
Quarter-to-date availability for the Northstar environment is 99.82%.
Completed countries are stable under the current support model.
No lost alerts were reported in the QBR review period.
Operations evidence is improving, with remaining work focused on consistency across open countries.
Aurora Dynamics will continue reporting availability, action aging, and firmware distribution in the weekly pack.

## Slide 7
Phase 3 roadmap
Confirm Italy regulatory approval path and decision date.
Select the Phase 3 sequencing approach that protects scope and operating quality.
Complete evidence-pack normalization for remaining country sign-off.
Fold firmware upgrades into local cutover windows.
Prepare steering materials with progress, risk movement, and value evidence.

## Slide 8
Delivery risks and mitigations
Italy approval remains the critical external dependency and has a named escalation owner.
Reporting evidence inconsistency is being addressed through a single acceptance template.
Firmware 3.4.2 exposure is manageable through planned maintenance windows.
Data validation exceptions are reviewed daily until disposition is stable.
Amber status will be revisited if a decision point passes without an agreed mitigation.

## Slide 9
Customer asks
Confirm Meridian Bank owner for final acceptance evidence review.
Support the Italy regulatory escalation with the requested evidence package.
Validate the preferred format for quantified downtime avoidance in EUR.
Agree whether Phase 3 should proceed under the sequential recommendation if approval remains open.
Keep local operations contacts available for cutover readiness checks.

## Slide 10
Next steps
Aurora Dynamics will send the updated action register after the QBR.
Priya Raman will coordinate the Italy evidence package and sequencing recommendation.
Ava Nakamura will prepare the quantified value narrative for the September governance pack.
Rajiv Menon will confirm operations reporting ownership for remaining countries.
The joint team will use the weekly status pack as the single source for progress and risks.