AURORA DYNAMICS

Project Northstar August QBR Meeting Notes

Meridian Bank and Aurora Dynamics — Wed 12 Aug 2026

See the failure before it happens.

Meeting context

Date: Wed 12 Aug 2026. Forum: Project Northstar August QBR. Customer attendees: Helena Vargas, Head of Infrastructure; Rajiv Menon, IT Operations Manager. Aurora attendees: Ava Nakamura, Account Executive; Priya Raman, Delivery Manager.

The August QBR reviewed deployment progress, service performance, value evidence, and the decision path for Phase 3. Meridian Bank acknowledged that completed countries are stabilizing, but asked Aurora Dynamics to make the business value narrative more quantified and easier to reuse in executive updates.

Discussion summary

Priya Raman explained why the overall status remains Amber. The deployment factory is functioning, and nine countries have moved into handover, but Italy regulatory approval could still affect the final sequence. Rajiv Menon asked that acceptance evidence be made more consistent so local operations teams can use it without reinterpretation.

Helena Vargas asked for a stronger connection between the operational rollout and financial value. Ava Nakamura agreed that the next pack should quantify downtime avoidance in EUR, using clear assumptions that Meridian Bank can approve or challenge. The team agreed not to issue a separate commercial note; the item belongs in the next governance pack.

Decisions

| # | Decision | Owner | Date |
| --- | --- | --- | --- |
| 1 | Use sequential planning as the fallback for Phase 3 if Italy approval is not confirmed by the next governance checkpoint. | Helena Vargas | 12 Aug 2026 |
| 2 | Keep the customer-facing status at Amber while mitigation owners and dates remain credible. | Priya Raman | 12 Aug 2026 |
| 3 | Move financial-value evidence into the September steering pack rather than issuing a separate note. | Ava Nakamura | 12 Aug 2026 |

Open actions

| ID | Action | Owner | Due date | Status |
| --- | --- | --- | --- | --- |
| A-01 | Customer requested quantified downtime avoidance in EUR — Aurora to revert | Ava Nakamura | 26 Aug 2026 | Open / overdue |
| A-02 | Provide sample acceptance evidence pack for completed countries. | Priya Raman | 19 Aug 2026 | Open |
| A-03 | Confirm operations reporting owner for the remaining rollout countries. | Rajiv Menon | 21 Aug 2026 | Open |
| A-04 | Validate Italy approval evidence list and escalation route. | Priya Raman | 28 Aug 2026 | Open |
| A-05 | Share proposed September QBR agenda and customer asks. | Ava Nakamura | 2 Sep 2026 | Open |

Follow-up tone

The customer tone was supportive but specific. Helena Vargas wants executive-ready value evidence, while Rajiv Menon wants operating controls that his team can sustain. Follow-up should therefore be concise, quantified, and grounded in the same deployment numbers used in the weekly status report.

No attendee requested a change to contracted scope. The open concern is sequencing risk, not solution fit. Priya Raman will continue to anchor the action review until the Italy approval path is clear and the reporting evidence pack is accepted.