## Options
Purpose
Compare Phase 3 approaches for Project Northstar and identify the path that protects scope, quality, and customer confidence.
Option | Approach | Duration | Cost (USD) | Risk exposure | Dependency on Italy regulatory approval | Recommendation
Option A | Parallel rollout | 18 weeks | 1900000 | High: cross-country work overlaps and schedule float is limited. | Collapses if Italy is delayed. | Not recommended
Option B | Sequential rollout | 24 weeks | 1600000 | Moderate: longer duration, stronger control of acceptance gates. | Survives an Italy delay by resequencing work. | Priya's recommendation
Option C | Reduced scope | 14 weeks | 1100000 | Commercially high despite lower delivery load. | Avoids some dependency by removing work. | Not recommended; falls short of contracted scope

## Assumptions
Assumption area | Working assumption
Scope baseline | Project Northstar remains a 14-country, 3,200-asset deployment for Meridian Bank.
Progress baseline | Current deployment baseline is 1,870 assets complete out of 3,200.
Quality gate | Each country must complete telemetry validation, alert routing, acceptance evidence, and operations handover.
Italy dependency | Italy regulatory approval is unresolved and cannot be treated as a team-controlled task.
Financial treatment | Costs are delivery estimates in USD and do not alter the USD 4.2M / 3 years contract.
Recommendation logic | The recommendation preserves contracted scope and operating quality over the shortest calendar path.
Recommendation note
Option B is Priya Raman's recommendation because it survives an Italy delay while preserving the contracted country and asset scope.