AURORA DYNAMICS

NS Status Report W-1

Project Northstar — Mon 31 Aug to Sun 6 Sep 2026; issued Mon 7 Sep 2026

See the failure before it happens.

Weekly status report

Executive headline: Project Northstar remains Amber. Delivery momentum is visible in the completed estate, but the remaining path depends on closing the Italy regulatory approval dependency and normalizing evidence for the remaining country groups.

Executive summary

Project Northstar has reached 1,870 deployed assets out of the contracted 3,200-asset scope, which is 58% complete. Nine of fourteen countries have completed deployment and are operating under the agreed handover model. The completed estate is stable enough for Meridian Bank operations teams to use the runbook without routine Aurora-led intervention, which is the clearest sign that the deployment model is maturing.

Availability quarter to date: 99.82%. The figure is included as a delivery-management indicator for the Northstar environment and will continue to be reported in the weekly status pack. During the W-1 reporting week there were no lost alerts and no newly opened severity-one customer escalation.

The overall RAG remains Amber because the work is progressing but the schedule has less float than planned. Italy regulatory approval is unresolved, and inconsistent acceptance evidence across the remaining countries could slow sign-off. Priya Raman is holding the status at Amber rather than Red because mitigations, owners, and decision dates are clear.

Firmware adoption continues to move toward the standard branch. Version 3.6.0 is active on 1,230 assets, while 640 assets remain on 3.4.2. The remaining 3.4.2 group is tied to local access windows and is not a separate technical blocker.

Progress by country

The table reconciles the fourteen-country plan against actual deployed assets. Country labels are operational labels used for the delivery pack; Italy is shown explicitly because it is the active regulatory blocker.

| Country | Planned | Actual | Status | Blocker |
| --- | --- | --- | --- | --- |
| Country 01 | 250 | 250 | Complete | None |
| Country 02 | 220 | 220 | Complete | None |
| Country 03 | 200 | 200 | Complete | None |
| Country 04 | 190 | 190 | Complete | None |
| Country 05 | 180 | 180 | Complete | None |
| Country 06 | 170 | 170 | Complete | None |
| Country 07 | 160 | 160 | Complete | None |
| Country 08 | 155 | 155 | Complete | None |
| Country 09 | 145 | 145 | Complete | None |
| Italy | 520 | 0 | Blocked | Regulatory approval pending |
| Country 11 | 340 | 90 | In progress | Local maintenance window sequencing |
| Country 12 | 280 | 60 | In progress | Site access batching |
| Country 13 | 220 | 35 | In progress | Firmware staging queue |
| Country 14 | 170 | 15 | At risk | Data validation exceptions |

Completed countries have passed telemetry validation, alert routing, acceptance evidence review, and operations handover. The open countries are being managed through a tighter weekly cutover rhythm so that site access, firmware staging, and reporting evidence do not compete for the same customer reviewers.

Milestones

| Milestone | Target | Status | Management note |
| --- | --- | --- | --- |
| Wave 2 closeout | 28 Aug 2026 | Complete | Nine countries accepted into steady-state operation. |
| W-1 progress checkpoint | 7 Sep 2026 | Complete | Actual deployment reconciled at 1,870 assets. |
| Italy approval decision | 11 Sep 2026 | At risk | External decision remains the critical path. |
| Phase 3 sequencing decision | 15 Sep 2026 | Planned | Sequential fallback remains the recommended mitigation. |
| Customer steering update | 18 Sep 2026 | Planned | Pack will include progress, risk movement, and customer asks. |

Risks

| ID | RAG | Risk | Impact | Owner | Next control |
| --- | --- | --- | --- | --- | --- |
| R-03 | Red | Italy regulatory approval remains unresolved. | Late approval can force resequencing and compress acceptance. | Priya Raman | Escalate evidence pack for 11 Sep review. |
| R-07 | Red | Acceptance and reporting evidence is inconsistent across remaining countries. | Customer may delay formal sign-off if evidence packs differ. | Rajiv Menon | Approve one evidence template by 10 Sep. |
| R-09 | Amber | Firmware 3.4.2 population remains active in constrained sites. | Upgrade work may extend local support effort. | Priya Raman | Fold upgrades into agreed maintenance windows. |
| R-11 | Amber | Data validation exceptions in Country 14 may slow cutover. | Potential rework in mapping and acceptance testing. | Aurora delivery team | Daily exception review until stable. |

Open actions

| Action | Owner | Due date | Status |
| --- | --- | --- | --- |
| Confirm Italy approval escalation path and evidence pack. | Priya Raman | 8 Sep 2026 | Open |
| Provide Meridian Bank with standard reporting-evidence template. | Rajiv Menon | 10 Sep 2026 | Open |
| Reconcile firmware 3.4.2 upgrade windows with local site access. | Priya Raman | 11 Sep 2026 | Open |
| Prepare steering update with progress, risk, and decision ask. | Ava Nakamura | 14 Sep 2026 | Open |
| Validate Country 14 mapping exceptions and disposition. | Aurora delivery team | 9 Sep 2026 | Open |

Next week's plan

- Close the Italy evidence pack and confirm whether Phase 3 should proceed under the sequential fallback plan.

- Normalize acceptance evidence so every remaining country uses the same sign-off structure.

- Move the active firmware 3.4.2 list into country cutover planning rather than exception reporting.

- Prepare the Meridian Bank steering pack with clear owners, dated asks, and quantified value evidence.

- Keep the RAG at Amber unless the Italy decision point passes without an agreed mitigation.

Operating commentary

The joint team is spending less time debating status and more time resolving blockers. Daily reviews now separate true delivery constraints from routine cutover noise, and the single action register is reducing duplicate requests to Meridian Bank reviewers. This operating discipline is important because the remaining work has narrower schedule margins.

Customer sentiment remains constructive. Helena Vargas is focused on executive confidence and value evidence, while Rajiv Menon is focused on practical handover controls for operations teams. The next update should balance progress with direct asks so the customer can remove external blockers without re-opening already agreed scope.

No change is requested to the contracted scope. If the Italy dependency remains unresolved, the recommended response is to change sequence, preserve quality gates, and avoid any shortcut that weakens the final operating model. This keeps delivery aligned with the Phase 3 options analysis and the customer QBR discussion.